## Sheet1
Week beginning
Task/Deliverable | Responsibility | 2017-03-06 |  |  | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03
Determine Requirements | All
Research on community | All
Need identification | All
Problem definition | All
Objectives and constraints | All
Plan for fabrication and testing of a prototype | Braeden & Spencer
Detailed research on problem definition | All
Concept generation | All
Prepare slides for SRP1 | Zoee
Status Report Presentation 1 | All
Concept evaluation | Nicole
Concept selection | All
Write preliminary report | All
SOTA Report | Each individual
Preliminary Design Report | All
Create model | Nicole & Zoee
Project Plan (Gantt Chart) | Nicole
Concept Generation | All
Design Review 1
Concept Selection | All
Part Specification | Nicole
CAD Models | Rachelle/Zac
Software Development | Matt
Design Review 2
Build Initial Prototype | All
Testing and Iterations | All
Design Showcase
Compile PDF | All/TBD
Final Design Report
|  |  | Tasks | Deadlines/Deliverables